Item Requirements

Article Name: Additive Manufacturing of Copper Alloy Test Article Using Single-mode Continuous Green Laser Powder Bed Fusion (PBF) Equipment

1. Overview

- This task involves manufacturing a test article using copper alloy powder through powder bed fusion (PBF) additive manufacturing technology employing a single-mode continuous green laser, and conducting material property evaluations on the fabricated specimen.

2. Contract Method

- Contract Period: Ninety (90) days after Effective Date of Contract (EDC)

- Estimated Budget: USD 18,350.00

- Method of Contract: restricted competitive bid (the lowest bid price)

- Qualification bidding documents (must be submitted by the bidding deadline and verified prior to bid opening/qualification review)

  - Evidence of technical capabilities for task execution (patents related to Green Laser PBF equipment)

  - Test report for copper alloy (CuCrZr) manufactured using in-house equipment (meeting Requirement 1 specified in Section 3.3) 3. Detailed Task Description

3.1 Design/Manufacturing Plan Preparation & Kick-off Meeting 
(within 2 weeks after contract)

- Submit production design and schedule after discussing task details.

- Specify inspection items, methods (including equipment and standards), and performing agencies (or company) for test article and specimens.

- Hold a kick-off meeting to discuss details after establishing the manufacturing process and schedule.

- Proposed Master Plan (The manufacturer must submit a detailed plan)

  - 26.06
- Prepare detailed Design/Manufacturing plan prior to contract signing.
- Conduct kick-off meeting immediately after contract signing (discuss proposed Design/Manufacturing plan).
- Document and report DfAM/analysis results, followed by meeting.
- Start additive manufacturing after finalizing the printing geometry.

  - 26.07
- Perform inspection and measurement after additive manufacturing completion, submit results report.
- Begin post-processing and prepare for strength/leak testing (share progress by stage).
- Perform specimen testing and submit results analysis report.

  - 26.08
- Perform strength/leak testing (request client's on-site visit and observation) and ship delivery items to client.

3.2 DfAM Geometry and Process Design

- Review AM feasibility using 3D CAD model provided by the client.

- Perform DfAM(design for additive manufacturing) geometric design for the final design proposal and share model file (.prt, .stp, .stl, etc.).

- Predict deformation via simulation prior to printing.

- Establish strategies to minimize deformation (support, orientation, process parameters, compensation design, etc.).

- Create machining drawings for interface work after printing.

- The DfAM process and results must be documented and approved by the client before proceeding with additive manufacturing. Additive manufacturing must be able to initiate within two weeks of receiving approval for the documented DfAM design. The start of additive manufacturing must occur within one month of contract execution.

- Discuss design changes required for AM and finalize the design.

3.3 Additive Manufacturing(L-PBF)

- Deliverable: test article, 1 set

- Dimensions: ~340 mm x Dia. 170 mm (Detailed drawings provided after contract).

- Material: CuCrZr (for PBF)

  - Secure material certificates and perform basic inspections (shape, composition, size distribution, flowability, etc.).

- Requirements:

  - Must be manufactured as a single piece using single-mode continuous green laser PBF equipment, through a process satisfying the following conditions: density 99.98%, tensile strength 510MPa, yield strength 410MPa, elongation at break 20% (test in accordance with ASTM E8).

  - Using a single-mode continuous green laser PBF printer, print 4 round bars for tensile testing (same height as the test article) simultaneously with the test article (2 inside, 2 outside the test article).

  - Submit photos and videos documenting the entire process (printing, machining, inspection, measuring, test, etc.), with the video submitted as a time-lapse video (30~60 seconds).

3.4 Post-Processing

- Powder Removal & Inspection:

  - Completely remove internal powder before additional work, verify via RT (Radiographic Test) and CT (Computed Tomography).

  - Submit powder removal results (RT, CT video-based report) for approval. Check for defects like Shrinkage Lines (SL) or Pin Holes via visual inspection.

  - Proceed with re-manufacturing or follow-up processes upon agreement with the client depending on defects.

  - Measure dimensions in the as-printed state and submit a comparison report against the 3D CAD model used for printing and build simulation result.

- Stress Relief & Wire Cutting:

  - Perform sandblasting, stress relief heat treatment, and wire cutting according to the manufacturer's standards.

  - Remove supports from the test article before/after wire cutting.

- Strengthening Heat Treatment & Tensile Testing:

  - Perform heat treatment on the test article and round bars according to the manufacturer's standard for CuCrZr heat treatment.

  - Machine 4 tensile specimens per one round bar (number may vary based on SL location).

  - Machine the specimens so that the layer where SL or other defects are identified becomes the measurement location for the tensile test.

  - Perform the tensile test (at room temperature).

  - Test tensile specimens using tensile testing equipment within its inspection validity period, as specified in the manufacturing plan proposal and confirmed at the manufacturing kick-off meeting (If equipment is changed, a written justification must be submitted and approved by the client.).

  - The tensile test results are submitted to the client in report format (including tables and graphs).

  - Criteria: Individual tensile test results must achieve at least 90% of the reference values. Results below 90% are deemed manufacturing defects, requiring agreement with the client to determine subsequent process actions. Reference values may be adjusted to target values provided by the manufacturer with the client's approval.

- Test Article Inspection & Machining:

  - Perform additional visual inspection (including inner wall) and sandblasting for surface roughness improvement after separation from BP.

  - Perform dimensional measurements (using a coordinate measuring machine, CMM) on wire-cut test article to verify machining reference surfaces.

  - Based on the measured dimensions, revise the machining drawings (including tool drawings), obtain approval from the client, and perform the shape machining. After machining is complete, perform dimensional measurement (using a 3D measuring machine, CMM) on the machined areas.

  - If measurements are to be performed using equipment possessing equivalent precision instead of CMM, approval from the client must be obtained.

3.5 Assembly & Testing

- Assembly:

  - Secure fittings and caps, and mount them on the test article after machining is complete to enable testing.

  - The contractor must also prepare all necessary fittings, plugs, gaskets, pressure strength/leak test plugs and fixtures for the test article, and fastening bolts/nuts for the test article ports.

- Strength & Leak Testing:

  - Strength Test: Pressurize both flow path to 10 bar each (maintain at 10 bar intervals for 60 seconds each, avoid rapidly increasing pressure in one flow path to prevent hardware damage), then pressurize to 90 bar and maintain at 90 bar for 5 minutes. Attach dial gauges to measure deformation.

  - Leak Test 1: Pressurize both flow path to 10 bar each (maintain at 10 bar increments for 60 seconds each, avoid rapid pressure increases in one channel to prevent hardware damage), then pressurize to 60 bar and hold for 5 minutes to verify leak tightness (check internal pressure measurement or presence of bubbles in the water tank, etc.).

  - Leak Test 2: Pressurize flow path to 10 bar (maintain at 10 bar increments for 60 seconds each, avoid rapid pressure increases in flow path to prevent hardware damage), then pressurize to 30 bar and hold for 5 minutes to verify leak tightness (check internal pressure measurement or presence of bubbles in the water tank, etc.). This test is performed individually for each flow path (to verify the absence of leakage between flow paths).

  - Strength/leak tests shall be conducted in principle by preparing a test procedure sheet, obtaining approval prior to the test date, and performing the test in the presence of the client(preferably visit the manufacturer during 3D printing or strength/leak testing). If client attendance is not possible, the test process shall be captured and recorded, and the video provided.

  - The strength test involves placing the test article on a stable surface and attaching dial gauges or similar devices to areas susceptible to deformation to measure the amount of deformation.

3.6 Delivery

- After production and testing are completed, the test article must be completely dried to remove all internal and external moisture. It must then be filled with helium (or nitrogen) or equivalent protective measures must be taken to prevent moisture ingress.

- Pack securely to prevent damage during transport.

- Deliver all components used in the strength/leak test, including the caps and fasteners.

- Submit original manufacturing drawings and photographic documentation as original files.

- Submit the original data for all measurements, instrumentation, and tests.