New Oversea Ground Site

Pre-specification

- General description

Korea Aerospace Research Institute (KARI) is performing the Micro-Satellite Constellation Program, and as a part of the program, KARI is planning projects of new oversea operation site development. In these projects, the contractor shall take all the responsibilities of completely manufacturing, delivery, installation, performance verification of new antenna systems.

- Development schedule

The System Final Acceptance Test shall be occurred no later than June in 2029.

| June, 2026 [TBD] | Completion of FAT(Factory Acceptance Test)(#1) at manufacture |
| --- | --- |
| Aug, 2026 [TBD] | Installation of Antenna systems(#1) on site |
| Sept, 2026 [TBD] | Completion of OSAT(On-Site Acceptance Test) (#1) |
| June, 2027 [TBD] | Completion of FAT(Factory Acceptance Test) (#2) at manufacture |
| Aug, 2027 [TBD] | Installation of Antenna systems(#2) on site |
| Sept, 2027 [TBD] | Completion of OSAT(On-Site Acceptance Test) (#2) |
| June, 2028 [TBD] | Completion of FAT(Factory Acceptance Test) (#3) at manufacture |
| Aug, 2028 [TBD] | Installation of Antenna systems(#3) on site |
| Sept, 2028 [TBD] | Completion of OSAT(On-Site Acceptance Test) (#3) |
| June, 2029 [TBD] | System Final Acceptance Test (3 Antenna System Trial Run) |

*Developments Schedule could be changed.

- Delivery Site Information

Oversea Ground Site is yet to be determined, But the expected candidate site are as follows

Antenna system shall the delivery at the candidate site directly after FAT (Factory Acceptance Test) at Manufacture due to developments plan

- Candidate Site #1: West Australia

- Candidate Site #2: South Africa

- Candidate Site #3: Europe (SPAIN)

- Summary of Requirements for one of Antenna & RADOME

| Quantity | 1 system |  |
| --- | --- | --- |
| Diameter | Above 5 meter |  |
| X-band | G/T | Above >30.0 dB/K (with RADOME & Additional Filter) |
|  | Polarization | LHCP & RHCP Simultaneous |
|  | Frequency | Rx 8000~8400MHz with Additional Filter |
| S-band | G/T | >15.5 dB/K (with RADOME & Additional Filter) |
|  | Rx Polarization | LHCP & RHCP Simultaneous |
|  | EIRP | Above 54dBW |
|  | Tx Polarization | LHCP & RHCP Selectable |
|  | Frequency | Rx 2,200 ~ 2,290MHz with Additional Filter Tx 2,010 ~ 2,110MHz with Additional Filter |
| Tracking Operations | Program Track or Auto tracking |  |
|  | S-Band or X-Band Auto tracking Selectable |  |
| Accuracy | 0.015° rms |  |
|  | 0.050° rms |  |
| Position | LEO > 300 km attitude Az Velocity must be above 14deg/s Elevation and Train axis Velocity must be above 10deg/s No Keyholes : During zenith passes, No keyhole 90deg pass at 300km orbit |  |
| RADOME | Above 8.8meter Recommend manufactured in S.KOREA |  |

- Summary of Requirements for two of Antenna & RADOME

| Quantity | 2 systems |  |
| --- | --- | --- |
| Diameter | Above 7 meter |  |
| X-band | G/T | Above >33.0 dB/K (with RADOME & Additional Filter) |
|  | Polarization | LHCP & RHCP Simultaneous |
|  | Frequency | Rx 8000~8400MHz with Additional Filter |
| S-band | G/T | >19.6dB/K (with RADOME & Additional Filter) |
|  | Rx Polarization | LHCP & RHCP Simultaneous |
|  | EIRP | Above 57dBW |
|  | Tx Polarization | LHCP & RHCP Selectable |
|  | Frequency | Rx 2200~2290MHz with Additional Filter Tx 2010~2110MHz with Additional Filter |
| Tracking Operations | Program Track or Auto tracking |  |
|  | S-Band or X-Band Auto tracking Selectable |  |
| Accuracy | 0.015° rms |  |
|  | 0.050° rms |  |
| Position | LEO > 300 km attitude Az Velocity must be above 14deg/s Elevation and Train axis Velocity must be above 10deg/s No Keyholes : During zenith passes, No keyhole 90deg pass at 300km orbit |  |
| RADOME | Above 16meter Recommend manufactured in S.KOREA |  |